## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
US01 | Create TA Profile | As a TA applicant, I want to create a personal profile so that the school can record my basic information. | High (Must) | 1 | 1. Fields: Name, Student ID, Email, Skills. 2. Data is saved to a local .txt or .json file. | 5 | Core foundational feature. | 2026-03-08 | 2026-03-15
US02 | Upload CV | As a TA applicant, I want to upload my CV so that I can provide detailed background information. | High (Must) | 1 | 1. User can specify a file path. 2. The file path is linked to the user's profile in the text database. | 3 | Essential for recruitment. | 2026-03-10 | 2026-03-18
US03 | Post TA Job | As a Module Organiser (MO), I want to post a new TA position so that students can see the vacancy. | High (Must) | 1 | 1. Fields: Module Name, Requirements, Deadline. 2. Job details are persisted in a text-based format. | 5 | Primary value for MOs. | 2026-03-12 | 2026-03-20
US04 | Find & Apply Jobs | As a TA applicant, I want to search and apply for available jobs so that I can be considered for the role. | Medium (Should) | 2 | 1. Applicant can view a list of jobs. 2. Clicking 'Apply' creates an application record with 'Pending' status. | 5 | Links TA and MO roles. | 2026-03-23 | 2026-03-30
US05 | Select Applicants | As a Module Organiser (MO), I want to select specific applicants for jobs so that the recruitment is finalised. | Medium (Should) | 2 | 1. MO can view a list of applicants for their job. 2. MO can update status to 'Accepted' or 'Rejected'. | 3 | Completes the recruitment loop. | 2026-03-25 | 2026-04-05
US06 | Check Workload | As an Admin, I want to check the overall workload of TAs to ensure fair distribution. | Low (Could) | 3 | 1. Display total assigned hours per TA. 2. Highlight TAs exceeding the maximum allowed workload. | 8 | Important for management. | 2026-04-13 | 2026-04-25
US07 | Skill Matching (AI) | As an MO, I want the system to suggest candidates based on skill matching so that I can find the best fit. | Low (Could) | 4 | 1. Compare applicant keywords with job requirements. 2. Provide explainable matching results. | 13 | Optional AI-powered feature. | 2026-05-01 | 2026-05-15
US08 | Search & Filter Jobs | As a TA, I want to search and filter available jobs by skills or module code, so that I can quickly find positions that match my expertise. | Medium (Should) | 2 | 1. Given I am on the job list page, when I enter a keyword or select a skill filter, then the system should only display matching jobs. 2. Given no jobs match, then display a "No jobs found" message. | 3 | Enhances TA job finding experience. | 2026-03-23 | 2026-04-05
US09 | Withdraw Application | As a TA, I want to withdraw my application before a decision is made, so that I can manage my commitments if my availability changes. | Medium (Should) | 2 | 1. Given my application is "Pending", when I click "Withdraw", then the status changes to "Withdrawn". 2. Given the application is already accepted/rejected, the "Withdraw" button should be hidden. | 2 | Allows TAs flexibility in application. | 2026-03-23 | 2026-04-05
US10 | Status Notifications | As a TA, I want to receive a system notification when my application status changes, so that I am immediately aware of the outcome. | Low (Could) | 3 | 1. Given an MO accepts or rejects my application, when I log in, then I should see a notification alert. 2. The notification should clearly state the job title and the new status. | 3 | Keeps TAs updated on their status. | 2026-04-06 | 2026-04-19
US11 | Manage Job Postings | As an MO, I want to edit or close an existing job posting, so that I can update requirements or stop receiving applications when the quota is filled. | High (Must) | 2 | 1. Given I own the job posting, when I click "Close", then its status changes to "Closed" and TAs can no longer apply. 2. Given I edit a job, the updated details are saved and visible immediately. | 3 | Crucial for MOs to manage recruitment cycle. | 2026-03-23 | 2026-04-05
US12 | Export Applicant List | As an MO, I want to export the list of applicants for my module to a text/CSV file, so that I can review them offline. | Medium (Should) | 3 | 1. Given I view the applicants list, when I click "Export", then a CSV file containing applicant names and emails is downloaded. | 5 | Offline review capability for MOs. | 2026-04-06 | 2026-04-19
US13 | Export Workload Report | As an Admin, I want to export the overall TA workload report to a text/CSV file, so that I can use it for school administrative records and payroll. | Medium (Should) | 3 | 1. Given I view the workload dashboard, when I click "Export All", then a CSV file with all TAs' total working hours is downloaded. | 5 | Administrative compliance and payroll tracking. | 2026-04-06 | 2026-04-19
US14 | View Activity Logs | As an Admin, I want to view system activity logs, so that I can monitor usage and troubleshoot any access issues. | Low (Could) | 4 | 1. Given I am an Admin, when I access the Log tab, then I can see a list of recent logins and job postings. | 3 | Security and usage monitoring. | 2026-04-20 | 2026-05-15
US15 | AI Candidate Matching | As an MO, I want the system to use AI to calculate a match score between a job's requirements and an applicant's profile, so that I can easily shortlist the best candidates. | High (Must) | 4 | 1. Given an applicant applies, the system calls the AI module to compare job skills and TA skills. 2. A match score (e.g., 85%) is displayed next to the applicant's name in the MO's view. | 8 | Advanced AI feature for intelligent recruitment. | 2026-04-20 | 2026-05-15
US16 | AI Missing Skills | As a TA, I want the system to use AI to identify missing skills in my profile compared to jobs I am viewing, so that I know what to improve. | Medium (Should) | 4 | 1. Given I view a job I am not fully qualified for, the AI highlights the specific skills I lack based on my profile. | 5 | Advanced AI feature for TA skill development. | 2026-04-20 | 2026-05-15
US17 | AI Workload Flagging | As an Admin, I want the system to use AI to automatically flag TAs who have unbalanced workloads (overloaded or underutilized), so that I can ensure fair distribution of work. | Medium (Should) | 4 | 1. Given a TA's accepted hours exceed the school's maximum limit, the AI automatically tags them with an "Overloaded" warning on the Admin dashboard. | 5 | Advanced AI feature for Admin workload balancing. | 2026-04-20 | 2026-05-15